# Daily Construction Report

# 1. Climate

| Date | Weather | Wind force | Water level | Min/Max temp. |
| --- | --- | --- | --- | --- |
| Dec. 14, 2025 | Sunny | Breeze | 315.26 | 15℃/26℃ |

# 2. On-site Construction Activities

Daily Construction Statistics Table

| S/N | Construction Area | Activities | Quantities completed | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Right Bank Roads | Backfill of R10 Road with sand and gravel | 20m |  |
|  |  | Backfill of the road from Right Bank Abutment to Aggregate System with sand and gravel | 300m³ |  |
|  |  | Excavation of the road from Right Bank Abutment to Aggregate System | 300m³ |  |
| 2 | Explosives Magazine | Scaffold Assembly for Ammonium Nitrate Magazine | 1 item |  |
|  |  | Concrete Pouring for floor slab and partial drainage trench of Emulsion Explosives Magazine | 1 item |  |
|  |  | Laying of Waterproof Plastic Membrane, and Concrete Pouring for floor slab and partial drainage trench of Detonator Magazine | 19m³ |  |
| 3 | Right Bank Aggregate System | Rock Excavation for the main platform at EL.480 of the 1st Screening Workshop and 2nd Crushing Workshop | 6500m³ | Night Shift |
|  |  | Backfill and compaction for Finished Product Bin and loading platform at EL.450 | 6500m³ | Night Shift |
|  |  | Rock Excavation for the main platform at EL.480 of the 1st Screening Workshop and 2nd Crushing Workshop | 2500m³ | Day Shift |
|  |  | Backfill and compaction for the road below EL.506 of the primary crushing workshop, and for the Finished Product Bin and loading platform at EL.450 | 2500m³ | Day Shift |
|  |  | Earth Excavation for the access road to the 1st Screening Workshop at EL.480 | 1000m³ | Day Shift |
|  |  | Earth Excavation for the road at the finished product yard at EL.450 | 1500m³ | Day Shift |
|  |  | Compaction and backfill for Finished Product Bin and loading platform at EL.450 | 2500m³ | Day Shift |
|  |  | Slope cutting for the rear slope of the Receiving Platform at EL.537m | 1 item | Day Shift |
|  |  | Grouting for mortar anchor bolt holes and self-drilling anchor bolt holes on the berm of the rear slope of the Discharge Platform at EL.560-550m and on the rear slope of the Screening Workshop at EL.510-520m | 1 item | Day Shift |
|  |  | Acceptance inspection of mortar anchor bolt holes and self-drilling anchor bolt holes on the rear slope of the Screening Workshop at EL.510-520m | 1 item | Day Shift |
|  |  | Setting out of excavation boundary lines for the finished product yard, and staking for backfill and compaction of the loading workshop | 1 item | Day Shift |
| 4 | Right Bank Temporary Batching Plant 120(m³/h) | Curing of retaining walls for the aggregate bin | 1 item |  |
|  |  | Formwork Erection for retaining walls and partition walls of the aggregate bin | 30m² |  |
|  |  | Pouring of Weighbridge foundation | 6.2m³ |  |
| 5 | Right Bank Batching System | Earth Excavation | 5400m³ | Night Shift |
|  |  | Earth Excavation | 1728m³ | Day Shift |
|  |  | Gully Clearing and Grubbing | 1300m² | Day Shift |
|  |  | Earth Backfill and compaction | 1728m³ | Day Shift |
| 6 | R10 Road to 2# Spoil Area | Road Widening from R10 Road to 2# Spoil Area | 50m |  |
| 7 | Right Bank Abutment | Fabrication of rebar piles for the abutment | 4 units |  |
|  |  | Excavation of the abutment slope | 1000m² |  |
|  |  | Clearing and Grubbing of the downstream navigation channel slope | 1000m² |  |
|  |  | Filling of the water intake platform for water trucks with gravel | 150m³ |  |
| 8 | 22kV line | Electric Pole Erection on the Right Bank | 12 units |  |

# 3. On-site Manpower and Equipment

3.1. Manpower

| S/N | Staff type | Actual deployment |  |  | Remarks |
| --- | --- | --- | --- | --- | --- |
|  |  | Chinese | Foreign | Subtotal |  |
| I | Project management | 73 | 59 | 132 |  |
| 1) | Manager | 8 | 0 | 8 |  |
| 2) | Functional departments | 65 | 59 | 124 |  |
| II | Field Construction Personnel | 106 | 191 | 297 |  |
| 1) | Team Leader | 19 | 3 | 22 |  |
| 2) | Supervisor/Engineer | 9 | 0 | 9 |  |
| 3) | Technicians | 17 | 0 | 17 |  |
| 4) | Support / Administrative Staff | 3 | 0 | 3 |  |
| 5) | Skilled Laborer | 54 | 127 | 181 |  |
| 6) | Semi-skilled Worker | 0 | 3 | 3 |  |
| 7) | General Laborer | 4 | 58 | 62 |  |
| Total |  | 179 | 250 | 429 |  |

## 3.2. Equipment

| Equipment | Unit | Qty. | Running hrs. | Remarks |
| --- | --- | --- | --- | --- |
| Backhoe Excavator (1.0~2.0m³) | Set | 30 | 16h |  |
| Loader (3.0m³) | Set | 9 | 8h |  |
| 25t Dump Truck | Set | 49 | 16h |  |
| Bulldozer | Set | 6 | 8h |  |
| Road Roller | Set | 7 | 8h |  |
| Grader | Set | 6 | 8h |  |
| Water Truck | Set | 4 | 8h |  |
| Others | Set | 92 | / | Including equipment such as commuter vehicles, transport vehicles, emergency vehicles, emergency generators, etc. |
| Total | Set | 203 | / |  |

# 4. Records of Important Matters

| S/N | Content | Remarks |
| --- | --- | --- |
| 1 | / |  |

# 5. Environmental Health and Safety (EHS) Work

| S/N | Content | Remarks |
| --- | --- | --- |
| 1 | No safety hazards were identified during today's site operations |  |

# 6. Site Construction Pictures

| Earth Excavation for the Right Bank Batching System | Grouting for Slope Support of Right Bank Aggregate System |
| --- | --- |
| Clearing and Grubbing for Right Bank Abutment | Slope Trimming for the Right Bank Batching System |

# 7. Next day's Work Plan

| S/N | Construction Area | Activities | Planned Qty. | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Right Bank Batching System | Earthwork excavation |  |  |
| 2 | Right Bank Aggregate System | Earthwork excavation |  |  |

# 8. Pending Issues

| S/N | Content | Remarks |
| --- | --- | --- |
| 1 | / | / |

# 9. Barometer

| Period | Rainfall | Remarks |
| --- | --- | --- |
| / | / | / |

Recorded by: Liu Haosheng

Date: 2025/12/14